## Instructions
INSTRUCTIONS
RECURRENT EXPENDITURE ASSURANCE FRAMEWORK (REAF) - PROJECT REGISTRATION AND RISK SELF ASSESSMENT TOOL
Agencies should register projects as early as possible in the project life cycle, ideally as soon as the project concept has been internally approved.
This form should be completed referring to the REAF policy. |  | Click here for REAF policy
Data should be entered ONLY in the "Data Entry" Tab: |  | Data Entry
A summary of relevant information from the NSW Gateway Policy (TPP 17-01) and the REAF (TPP 19-XX) is reproduced at the following Tabs:
TAB | CONTENTS
Appendix 1 | Description of project profile/risk criteria
Appendix 2 | Risk score matrix and criteria
Appendix 3 | Gateway Review Process
Appendix 4 | Application of Gateway Reviews/Health Checks/agency requested reviews under the REAF
1. Once this form is complete please save the file with a unique file name using the following convention:
REAF Project Risk Profile Tool_Agency_Project Name_version x.xls
Replace 'Agency' with your actual Agency Name & 'Project Name' with the actual project name.Version number should commence from 1, and should be updated for every re-submission.
2. Please send back the Excel spreadsheet along with any supporting documents.
3. Registration spreadsheet and supporting documents should be emailed to:
Gateway@treasury.nsw.gov.au
4. Please use the following format in the email subject field: Project Registration_Agency name_Project Name_version
5. You will receive formal advice when the risk tier and the assurance plan are approved by the Major Recurrent Advisory Group (MRAG).
For any enquiries on how to use this form email the NSW Treasury Gateway Team: |  |  | Gateway@treasury.nsw.gov.au

## Data Entry
Project Registration and Risk Assessment
Data Entry Form
Instructions: This sheet is for data entry only - refer to the "Instructions" tab of this workbook for more detail. Tips: Alt+ Enter to create a new paragraph in free text cells . Alt+7 ( using the numeric pad), followed by a space, to create bullet points in free text cells. Be brief in responses.
Key
unshaded | do not enter data
data entry field-freeform text-adjust row height to make all text visible
data entry field-select from dropdown list
calculated field-do not enter data
DATA ENTRY FORM
Step 1 | Project registration | Fill in shaded boxes only | Special Instructions
Q1.01 | Project /Program name
Use a clear and concise project or program name that is easily understandable for people outside the project. The project should be named identically in PRIME.
Q1.02 | Responsible Minister
If multiple Ministers specify lead agency or lead Minister
Q1.02a | If other, specify
Q1.03 | Lead Department
Nominate the Department leading the project/program
Q1.03a | If other, specify
Q1.04 | Project Sponsor
Ensures that the project is focused throughout its life on achieving its objectives and delivering a product that will achieve the forecasted benefits. Participates in Gateway Reviews and Health Checks. Ensures the project delivers value for money and meets the objectives of the business case and may request additional Gateway Reviews or Health Checks beyond those mandated by the RIAF.
Q1.04a | Project Sponsor Name
Q1.04b | Project Sponsor Title
Q1.04b | Project Sponsor Address
Q1.04c | Project Sponsor Phone
Q1.04d | Project Sponsor Email
Q1.05 | Links to a program or another project
Q1.05a | Part of a Wider Program: (state name)
Q1.05b | Interdependence with another project: (state name)
Q1.06 | Project description |  | Attach any available supporting documents if available such as project concept or initiation document, draft business case etc. [please attach executive summaries only]
Insert summary description
Q1.07 | Objectives
Insert summary of project/program objectives
Q1.08 | Expected strategic benefits
Insert summary of contribution to strategic benefits. These benefits would include internal and/or external outcomes.
Q1.09 | Funding approval
Q1.10 | Funding source
Q1.10a | Funding details
Insert any relevant comment regarding funding
Q1.11 | Funding conditions
Insert dot point summary of any conditions that have been attached to funding of the project/program
Q1.12 | Estimated Total Cost
Total cost of the project/program over first 4 years. Best estimate at current point in time.
Q1.12a | Estimated Cost - Infrastructure ($ million) [over first four years] |  | Leave blank if nil
Q1.12b | Estimated Cost - ICT ($ million) [over first four years] |  | Leave blank if nil
Q1.12c | Estimated Cost - Recurrent ($ million) [over first four years] |  | Leave blank if nil
| Estimated Total Cost ($million) |  | DO NOT ENTER. Calculation.
| ETC Band ($m) |  | DO NOT ENTER. Calculation.
Q1.13 | Project's Current Phase and Key Milestones
Q1.13a | Current Project phase
Current phase of the project as at submission date
Q1.13b | Key Project Milestones (e.g. Funding approval, Project Commissioning, Project Operationalisation etc.) with estimated dates
Insert key project milestones with estimated dates
Step 2 | Assessing the priority and preliminary risk potential | Fill in shaded boxes only | Special Instructions
Q2.01 | Level of Government Priority |  | This field must be completed
| Refers to the level and timing of project or program priority (refer to Appendix 1 for more guidance). |  | Insert very brief supporting and/or clarifying comments – including responses, only where appropriate, to the indicative questions to be considered in addressing the criteria [Appendix1]
Q2.01a | Explanatory Notes
Q2.02 | Interface Complexity Risk |  | This field must be completed
| The extent to which the project or program’s success will depend on the management of complex dependencies (refer to Appendix 1 for more guidance). |  | Insert very brief supporting and/or clarifying comments – including responses, only where appropriate, to the indicative questions to be considered in addressing the criteria [Appendix1]
Q2.02a | Explanatory Notes
Q2.03 | Procurement Complexity Risk |  | This field must be completed
| The extent to which a project or program requires, sophisticated, customised or complex procurement methods (refer to Appendix 1 for more guidance). |  | Insert very brief supporting and/or clarifying comments – including responses, only where appropriate, to the indicative questions to be considered in addressing the criteria [Appendix1]
Q2.03a | Explanatory Notes
Q2.04 | Agency Capability Risk |  | This field must be completed
| The extent to which the agency has demonstrated capability (skills and experience) for the type of project proposed i.e. the lower the agency capability the higher the risk (refer to Appendix 1 for more guidance). |  | Insert very brief supporting and/or clarifying comments – including responses, only where appropriate, to the indicative questions to be considered in addressing the criteria [Appendix1]
Q2.04a | Explanatory Notes
Q2.05 | Criticality of Service Risk |  | This field must be completed
| The extent to which a project or program requires is essential to meet a deficiency that would otherwise have serious adverse impact (refer Appendix 1 for more guidance) |  | Insert very brief supporting and/or clarifying comments – including responses, only where appropriate, to the indicative questions to be considered in addressing the criteria [Appendix1]
Q2.05a | Explanatory Notes
Q2.06 | Implementation Complexity Risk |  | This field must be completed
| The extent to which the project or program’s success will depend on the resolution of challenging industrial relations issues, significant reorganisation, and other risks (refer to Appendix 1 for more guidance). |  | Insert very brief supporting and/or clarifying comments – including responses, only where appropriate, to the indicative questions to be considered in addressing the criteria [Appendix1]
Q2.06a | Explanatory Notes
Step 3 | Calculating the preliminary project risk tier | Do not enter - self calculated | Do not enter - self calculated
Q3.01 | Rating - Level of Government Priority | Level of Government Priority | -
Q3.02 | Rating - Interface Complexity | Interface Complexity Risk | -
Q3.03 | Rating - Procurement Complexity | Procurement Complexity Risk | -
Q3.04 | Rating - Agency Capability | Agency Capability Risk | -
Q3.05 | Rating - Criticality of Service Complexity | Criticality of Service Risk | -
Q3.06 | Rating -Implementation Complexity | Implementation Complexity Risk | -
Q3.07 | Total weighted score and corresponding risk range
Q3.08 | Preliminary Risk Tier
Step 4 | Additional Considerations & Adjustment to risk Tier | Fill in shaded boxes only | Special Instructions
Q4.01 | Are there any reasons why the Preliminary risk rating determined above should be adjusted to be higher or lower on account of any additional risk considerations? Additional factors that could impact risk rating include, for example, risk of reputational damage, unknown project governance arrangements, lack of necessary project development plan and/or delivery skills and resources and critical or mandated start or completion date. |  | Attach any supporting documentation if answer is Yes
Q4.01a | If Yes, please provide brief comments |  | Please identify all additional risks and proposed mitigating strategies
| Preliminary Risk Tier |  | DO NOT ENTER. Calculated above
Q4.02 | Based on the answer to Q4.01 does the Preliminary risk tier require to be adjusted?
Q4.03 | Adjusted Risk Tier |  | Use drop down box to select proposed adjusted tier if the answer to the preceding question is YES, otherwise leave blank
Use drop down ONLY if there is a need to adjust the preliminary risk tier (calculated at Step 3) - if relevant comment on rationale for adjusting the tier in Comment box Q4.01a.
Step 5 | Proposed Project assurance plan | Fill in shaded boxes only | Special Instructions
Q5.01 | Proposed independent assurance
Indicate Yes or No if Gate is required / Indicate approximate date if known.
Provide any overall comments on the proposed assurance plan
Q5.01a | Gate 0 - Project Justification (refer Appendix 3 and 4 for more detail)
Q5.01b | Month/Year or Q/Year
Q5.01c | Gate 1 - Strategic Alignment gate (refer Appendix 3 and 4 for more detail)
Q5.01d | Month/Year or Q/Year
Q5.01e | Gate 2 - Business Case gate (refer Appendix 3 and 4 for more detail)
Q5.01f | Month/Year or Q/Year
Q5.01g | Gate 3 - Pre-tender/Pre-execution gate (refer Appendix 3 and 4 for more detail)
Q5.01h | Month/Year or Q/Year
Q5.01i | Gate 4 - Tender Evaluation gate (refer Appendix 3 and 4 for more detail)
Q5.01j | Month/Year or Q/Year
Q5.01k | Gate 5 - Pre-Commissioning gate (refer Appendix 3 and 4 for more detail)
Q5.01l | Month/Year or Q/Year
Q5.01m | Gate 6 - Post-Implementation gate (refer Appendix 3 and 4 for more detail)
Q5.01n | Month/Year or Q/Year
Q5.02 | Proposed Gateway Health Checks
Indicate any proposed independent Health Checks and estimated dates if known.
Q5.03 | Project Registration, Risk Tier and Assurance Plan Submitted by
Submitted in accordance with individual delivery Agency policy and delegations
Q5.03a | Project Registration, Risk Tier and Assurance Plan submitted by (Provide name)
Q5.03b | Title of Submitter
Q5.03c | Contact number of Submitter
Q5.03d | Email address of Submitter
Q5.04 | Project Registration, Risk Tier and Assurance Plan Approved by
Approval in accordance with individual delivery Agency policy and delegations
Q5.04a | Project Registration, Risk Tier and Assurance Plan approved by (Senior Responsible Officer with the delegation to approve submission of form)
Q5.04b | Title of Approver
Q5.04c | Contact number of Approver
Q5.04d | Date approved
Step 6 | Treasury Contact | Fill in shaded boxes only
Q6.01 | Engagement with Treasury
Q6.01a | Has this proposal been discussed with NSW Policy & Budget Treasury Analyst
Q6.01b | If yes, who is your Treasury Policy & Budget Analyst (Name)
THE END
RECURRENT EXPENDITURE ASSURANCE FRAMEWORK

## Appendix 1
APPENDIX 1 – Description of project profile/risk criteria
| Criteria | Sub-Criteria | Examples of questions to be considered when addressing the criteria
1 | Government priority: 15% The level and timing of project or program priority, where: • The level of priority for a project is specifically mandated (or where a Ministerial authority has been given to mandate that a project is a priority) in documents such as the NSW Budget, Premier’s Priorities, State Priorities, State Infrastructure Strategy, Election Commitment, or is a response to a Legislative Change. Alternatively, the project is an enabler of a mandated priority project. • The timing of the priority project can be either within or outside the Forward Estimates | Very High Government priority Priority Government project, and project will be fully operational within 12 months | Government Priority indicators • Has the project been specifically mandated in the NSW Budget? • Has the project been specifically mandated in the Premier's Priorities or equivalent? • Is the project linked to a project specifically mandated in any Government endorsed whole of Government plan, for example, the State Infrastructure Strategy? • Is the project an election commitment? • Is the project a response to a legislative change? • Is the project an enabler of a mandated priority project? • Has there been a Ministerial announcement regarding the project? • Has the project received significant regional or state-wide media coverage? • Is the project a strategic priority for Government? • Is the project a strategic priority for the agency or department? • Does accountability for the project reside with Cabinet, a Cabinet Committee or a Minister?
High Government priority Priority Government project, and project will be fully operational within the next 1-2 years of the forward estimates period
Medium Government priority Priority Government project, and project will be fully operational within the next 3-4 years of the forward estimates period
Low Government priority Priority Government project, and project will be commenced within the forward estimates period
|  | Very Low Government Priority Agency priority in Agency Strategic Plan over the next 10 years | Project timing indicators • Has planning or implementation of the project already commenced? • Will the project be fully operational within 12 months? • Will the project be fully operational within the forward estimates period?
Extremely Low Government priority Not a documented Government or agency priority
2 | Interface complexity: 15% The extent to which the project or program’s success will depend on the management of complex dependencies with other: • Institutions – certain bodies are contributing to the funding of the project or will be given operational responsibility. • Projects or services – there are fundamental interdependencies with other projects or services that will directly influence the scope and cost of the project. | Very high interface complexity risk Extensive interface and/or interdependence with other entities, projects, programs or services | Interface Complexity indicators • Are other entities contributing to the funding of the project? • Will other entities be given full or partial operational responsibility for the project? • Are there other projects, program or services that will directly influence the scope and cost of the project? • Does the project involve multi-agency delivery? • Are the anticipated project benefits dependent on another project, program or service? • Does the project involve significant integration (IT or otherwise) with other projects, programs or services? • Will members of the public be directly impacted by this project? • Will the private sector be directly impacted by this project? • Will the public sector (outside of the delivery agency) be directly impacted by this project? • Will the project involve external delivery partners?
High interface complexity risk Frequent interface and/or interdependency with other entities, projects, program or services
Medium interface complexity risk Some interface and/or interdependency with other entities, projects, programs or services
Low interface complexity risk Minor interface and/or interdependency with other entities, projects, programs or services
Very low interface complexity risk Very little or infrequent interface or interdependency with other entities,
Extremely low interface complexity risk No interface or interdependency with other entities, projects, programs or services
3 | Procurement Complexity: 20% The extent to which a project or program requires sophisticated, customised or complex procurement methods (non-traditional), thereby increasing the need for a careful assessment and management of risk. Procurement complexity may also be influenced by the extent of agency experience and capability. For example, complex procurement methods may be used more commonly by some agencies and represent a lower procurement risk. | Very high procurement complexity risk Highly complex procurement model | Procurement Complexity indicators • Will/could the project use a non-traditional (complex or customised) procurement method? • Does the agency have experience in the proposed procurement method? • Does the agency have a high level of capability in the proposed procurement method? • Is the service contract likely to be >10 years? • Is the project dependent on input from an immature/inexperienced market segment?
High procurement complexity risk Unconventional procurement model
Medium procurement complexity risk Some procurement complexity
Low procurement complexity Minor procurement complexity
Very low procurement complexity risk Business as usual procurement
Extremely low procurement complexity risk No procurement complexity.
| Agency capability: 20% The extent to which the sponsor agency has demonstrated capability (skills and experience), or can access through recruitment or procurement the required capability in the development and/or delivery of the type of project or program proposed and/or its delivery strategy. | Very high agency capability risk
High agency capability risk
Medium agency capability risk
Low agency capability risk
Very low agency capability risk
Extremely low agency capability risk
4 | Agency Capability (20%) The extent to which the sponsor agency has demonstrated capability (skills and experience), or can access through recruitment or procurement the required capability in the development and/or delivery of the type of project or program proposed and/or its delivery strategy. | Very high agency capability risk No projects of this type previously delivered over the last 10 years | Agency Capability indicators • Are the operations and outcomes of the project aligned to the agency's core business and strategic objectives? • Does the organisation have a successful track record of delivering initiatives of a similar scope and/or scale? • Has the organisation been established within the past 12 months? • Does the organisation have ongoing stable operations? • Does the organisation have an ongoing, stable source of funding? • Has the organisation been established for the purpose of delivering this project? • Has the organisation delivered a project that has been subject to a major recurrent Gateway review? • Has the agency delivered a recurrent, capital or ICT project/program that has been subject to a recurrent, capital or ICT Gateway? • Will the agency be delivering this project in partnership with a more experienced delivery partner? • Does the agency have in-house capability to deliver the project or will the agency be contracting/recruiting • Does the agency have the capability to manage the ongoing activities of the project after the procurement stage?
High agency capability risk Few projects of this type previously delivered over the last 10 years
Medium agency capability risk Several similar projects delivered over the last 5 years
Low agency capability risk Many similar projects delivered over the last 5 years
Very low agency capability risk Many similar projects delivered over the last 2 years
Extremely low agency capability risk Business as usual (routine)-No agency capability risk
5 | Criticality of Service : 15% The extent to which a project is essential to meet a deficiency that would otherwise have serious adverse impacts on the functioning of an existing community or the growth of a new community. | Very high impact on an essential service Addresses an urgent and critical deficiency that could have a highly adverse impact on an essential service | Criticality of Service indicators Does the project involve a service that impacts an existing community? • Does the project involve a service that impacts the development or growth of a new community? • Is the fulfilment of a legislative requirement dependent on this project? • Is the project considered crucial to the operation of the agency? • Would the failure of the project have significant implications for regional, state or national security? • Would the failure of the project have significant implications for the internal operations of the delivery agency?
High impact on an essential service Provides an enhancement or addresses a deficiency that could have a significant impact on the delivery of an essential service
Medium impact on an essential service Provides an enhancement or addresses a deficiency that could have a moderate impact on the delivery of an essential service
Low impact on an essential service Provides an enhancement or addresses a deficiency that could have a minor impact on the delivery of an essential service
Very Low impact on an essential Services Addresses minor deficiency that could have a very low impact upon service delivery
Extremely low impact on an essential service Not related to an essential service
6 | Implementation Complexity: 15% The extent to which the project’s success will depend on resolution in the agency of challenging industrial relations issues, significant re-organisation of functions or activities within the agency, relocation of functions or activities, changes of business processes and operational risk. | Very high implementation complexity There are a significantly high level of unknowns and/or assumptions involved which may have a significant influence over successful implementation | Implementation Complexity indicators • Does the project involve a significant organisation restructure to deliver services? • Does the project involve the relocation of existing functions or activities? • Does the project involve a significant change to business processes? • Does the project implementation affect existing industrial relations arrangements? • Does the project involve significant operational risk?
High implementation complexity There are a high level of unknowns and/or assumptions which may influence over successful implementation
Medium implementation complexity There are a moderate level of unknowns and/or assumptions involved which may influence successful implementation
Low implementation complexity There are a low level of unknowns and/or assumptions involved which are unlikely to influence the success of implementation
Very low implementation complexity There are a low level of unknowns and/or assumptions involved which are highly unlikely to influence the success of implementation
Extremely low implementation complexity There are little or no assumptions involved

## Appendix 2
APPENDIX 2 – Risk score matrix and risk profile criteria For Recurrent Expenditure above $100 million in 4 years or $50 million in any given year
Weighted | ETC Range |  |  |  | Criteria | Weighting | Criteria | Priority and Risk level | Score
Risk Score | >$500M | $250M – $500M | $100M – $250M | <$100 M | Government priority | 15% | Government priority | Very High Government priority | 5
4.1 – 5.0 | Tier 1 | Tier 1 | Tier 1 | Tier 1 | Interface complexity | 15% |  | High Government priority | 4
3.1 – 4.0 | Tier 1 | Tier 1 | Tier 2 | Tier 2 | Procurement complexity | 20% |  | Medium Government priority | 3
2.6 – 3.0 | Tier 2 | Tier 2 | Tier 2 | Tier 3 | Agency capability | 20% |  | Low Government priority | 2
2.1 – 2.5 | Tier 2 | Tier 2 | Tier 3 | Tier 4 | Criticality of Service | 15% |  | Very Low Government Priority | 1
0.0 – 2.0 | Tier 2 | Tier 3 | Tier 4 | Tier 4 | Implementation complexity | 15% |  | ExtremelyLow Government priority | 0
[7 empty] | Interface complexity | Very high interface complexity risk | 5
Note: <$100 M bracket also includes projects with an ETC under $100 M but >$50M in any one year and any projects nominated by ERC, the agency or NSW Treasury. | [7 empty] | High interface complexity risk | 4
[8 empty] | Medium interface complexity risk | 3
[8 empty] | Low interface complexity risk | 2
[8 empty] | Very low interface complexity risk | 1
[8 empty] | Extremely low interface complexity risk | 0
[7 empty] | Procurement complexity | Very high procurement complexity risk | 5
[8 empty] | High procurement complexity risk | 4
[8 empty] | Medium procurement complexity risk | 3
[8 empty] | Low procurement complexity risk | 2
[8 empty] | Very low procurement complexity risk | 1
[8 empty] | Extremely low sourcing complexity risk | 0
[7 empty] | Agency capability | Very high agency capability risk | 5
[8 empty] | High agency capability risk | 4
[8 empty] | Medium agency capability risk | 3
[8 empty] | Low agency capability risk | 2
[8 empty] | Very low agency capability risk | 1
[8 empty] | Extremely low agency capability risk | 0
[7 empty] | Criticality of Service | Very high impact on an essential service | 5
[8 empty] | High impact on an essential service | 4
[8 empty] | Medium impact on an essential service | 3
[8 empty] | Low impact on an essential service | 2
[8 empty] | Very Low impact on an Essential Services | 1
[8 empty] | Extremely low impact on an essential service | 0
[7 empty] | Implementation complexity | Very high implementation complexity risk | 5
[8 empty] | High implementation complexity risk | 4
[8 empty] | Medium implementation complexity risk | 3
[8 empty] | Low implementation complexity risk | 2
[8 empty] | Very low implementation complexity risk | 1
[8 empty] | Extremely low implementation complexity risk | 0
Office Use only below this line
Rating Lookup Table
[5 empty] | 0 | 0.0 – 2.0
[5 empty] | 2.1 | 2.1 – 2.5
[5 empty] | 2.6 | 2.6 – 3.0
[5 empty] | 3.1 | 3.1 – 4.0
[5 empty] | 4.1 | 4.1 – 5.0
tbllevelratings
[5 empty] | Level | Rating
[5 empty] | Extremely low | 0
[5 empty] | Very low | 1
[5 empty] | Low | 2
[5 empty] | Medium | 3
[5 empty] | High | 4
[5 empty] | Very high | 5

## Appendix 3
APPENDIX 3 – Gateway Review Process

## Appendix 4
APPENDIX 4 – Application of Gateway Reviews and Health Checks under the REAF
Agency registers and risk assesses the project and recommends a Project Assurance Plan with the recommended Gateway reviews that it plans to conduct. Major Recurrent Advisory Group (MRAG) reviews and approves the Project Assurance Plan with the final selection of Gateway reviews for each project depending on the risk rating, nature of the project and other considerations.
Health Checks are optional for all projects and should be identified as part of the Project Assurance Plan.
Delivery Agencies can nominate additional Gateway Reviews and Health Checks beyond those mandated by the Major Recurrent Assurance Framework.
Glossary
Gateway Review | A review of a project or program by an independent team of experienced practitioners at a specific key decision point (gate) in a project or program’s lifecycle. A Gateway Review is a short, focused, independent expert appraisal of the project or program that highlights risks and issues, which, if not addressed, may threaten successful delivery. It provides a view of the current progress of a project or program and assurance that it can proceed successfully to the next stage if any critical recommendations are addressed.
Gate | Particular decision point(s) in a project/program’s lifecycle when a Gateway Review may be undertaken.
Gate 0 (Justification) | Provides confidence that the proposal is aligned with the Government and Agency's strategic plans and the service identified warrants further consideration
Gate 1 (Strategic Alignment) | Strategic alignment gate. Assesses the robustness of the refined and scoped service need and whether the best value means of serving that need is proposed after consideration of a broad range of alternatives
Gate 2 (Business Case) | Business case gate. Assesses the robustness of the business case prior to approval
Gate 3 (Pre-Tender/Pre-execution) | Pre-execution gate. Assesses delivery readiness and includes pre-tender review (where relevant). Confirms a suitable procurement strategy has been selected and the project is ready to progress to the next stage
Gate 4 (Tender Evaluation) | Tender evaluation gate. Confirms the recommended decision appears appropriate before a contract is entered into and provides agency management with confidence that the process used to select the proposed service provider is robust.
Gate 5 (Pre-commissioning) | Pre-Commissioning. Assesses the state of readiness to commission the project and implement the change management required.
Gate 6 (Post-implementation) | Post-implementation, Confirms realisation or plan for realisation of benefits against those agreed at business case; ensures lessons learned have been sufficiently considered and documented.
Expert Review Team | A team of expert independent reviewers, sourced from the Expert Reviewer Panel engaged to undertake a Gateway Review or Health Check

## Print A (hidden)
Project Sponsor |  | Service need | Option analysis | Business Case | Pre-Tender | Tender | Pre-Commissioning | Post implementation
Project Sponsor Title
ETC ($m) ~
Current Project phase |  | G0 | G1 | G2 | G3 | G4 | G5 | G6
Key Project Milestones
Part of a Wider Program
Interdependence with another project
Agency Proposed Risk Tier
Executive Summary | Project Objectives
Funding | Expected Benefits
Funding Approval:
Source:
Funding Conditions:

## Print B (hidden)
Risk Criteria | Selection | Explanation | Score
Level of Government Priority |  |  | -
Interface Complexity Risk |  |  | -
Procurement Complexity Risk |  |  | -
Agency Capability Risk |  |  | -
Criticality of Service Risk |  |  | -
Implementation Complexity Risk |  |  | -
Risk Tier |  | Weighted score
Additional Consideration:
Adjusted risk tier |  |  | N/A
Explanatory notes for additional consideration
Note on D15: Pawana Krishnan: To be manually entered based on information provided in Step 4 of Data Entry sheet

## Print C (hidden)
Agency Proposed Risk Tier
Proposed independent assurance
Proposed Health Checks
For MRAG Discussion:
MRAG Action: Confirm Risk Tier and Assurance Plan

## Version control (hidden)
Version | Date | Changes
Project Risk Profile Tool_RIAF | 2017-03-14 | N/A - initial version
Project Risk Profile Tool_RIAF | 2017-03-16 | Additional protection and error messages
RIAF Project Registration and Risk Profile Tool | 2017-04-05 | Release version 1
RIAF Project Registration and Risk Profile Tool | 2017-06-05 | Minor errors corrected
RIAF Project Registration and Risk Profile Tool_June 2018 | 2018-06-14 | Added Print A, Print B and Print C sheets
RIAF Project Registration and Risk Profile Tool_Below 100m & above 10m_July 2018 | 2018-07-09 | Customised the risk tool for investments below $100m and above $10m
RIAF Project Registration and Risk Profile Tool_Sep 2018 | 2018-09-13 | Cut down unnecessary fields from the original risk tool
REAF Project Registration and Risk Profile Tool_Nov 2018 | 2018-11-20 | RIAF changed to REAF

## Drop down lists (hidden)
DROP DOWN LISTS
Responsible Minister | Department | Capital asset type | Project_program priority | ETC Band | Risk Potential | Yes/No | Yes/No | Yes/No/Maybe | Yes/No/Developed | Yes-in place/Being developed/No | Tier | Health Checks | Frequency | Check |  | Project phase | Funding approval
Attorney General | Education | 1. Infrastructure Project | State Budget Allocation | <$100 M | Extremely low | Yes | Yes | Yes | Yes | Yes-in place | Tier 1 | None | Monthly | P | Very high change complexity risk | Concept development | None approved
Minister for Aboriginal Affairs | Family and Community Services | 2. Property Development | Strategic Plan | $100M – $250M | Very low | No | No | No | No | Being developed | Tier 2 | 1 | Quarterly | O | High change complexity risk | Preliminary Business Case | Approved for development of Strategic Business Case
Minister for Aging | Finance, Services and Innovation | 3. Equipment | Election Commitment | $250M – $500M | Low |  | N/A | Possibly | Being Developed | No | Tier 3 | 2 | None |  | Medium change complexity risk | Business Case | Approved for development of Final Business Case
Minister for Corrections | Health | 4. ICT Project | Ministerial Commitment | >$500M | Medium |  |  | N/A | N/A |  | Tier 4 | 3 | Other |  | Lower change complexity risk | Pre-execution | Funding Approved
Minister for Counter Terrorism | Industry, Skills and Regional Development | 5. Other capital expenditure | Legislation |  | High | [6 empty] | Greater than 3 |  |  | Very low change complexity risk | Tender evaluation
Minister for Disability Services | Justice |  | Other |  | Very high | [6 empty] | Unknown |  |  | Extremely low change complexity risk | Pre-commissioning (build/test)
Minister for Early Childhood Education and Assistant Minister for Education | Planning and Environment | [14 empty] | Implementation
Minister for Education | Premier and Cabinet | [14 empty] | Closure
Minister for Emergency Services | Transport for NSW
Minister for Energy and Utilities | Treasury
Minister for Family and Community Services | Other
Minister for Finance, Services and Property
Minister for Health | [5 empty] | Funding Source |  |  |  | Example |  | Changetier | Yes | No
Minister for Heritage |  |  | Gate 0 - Project Justification |  |  | Budget funded-approved |  |  |  | selection 1 |  | Yes | Tier 1
Minister for Housing |  |  | Gate 1 - Strategic Assessment |  |  | Budget funded-to be approved |  |  |  | selection 2 |  | No | Tier 2
Minister for Industrial Relations |  |  | Gate 2 - Business Case |  |  | Agency funded |  |  |  | selection 3 |  |  | Tier 3
Minister for Innovation and Better Regulation |  |  | Gate 3 - Pre-Tender/Pre-execution |  |  | Partly Budget funded-approved | [6 empty] | Tier 4
Minister for Lands and Forestry |  |  | Gate 4 - Tender Evaluation |  |  | Partly Budget funded-to be approved
Minister for Local Government |  |  | Gate 5 - Pre-Commissioning |  |  | Other
Minister for Medical Research |  |  | Gate 6 - Post-Implementation
Minister for Mental Health
Minister for Multiculturalism
Minister for Planning
Minister for Police
Minister for Primary Industries
Minister for Racing
Minister for Regional New South Wales
Minister for Regional Water
Minister for Resources
Minister for Roads, Maritime and Freight
Minister for Skills
Minister for Small Business
Minister for Social Housing
Minister for Sport
Minister for the Arts
Minister for the Environment
Minister for the Prevention of Domestic Violence and Sexual Assault
Minister for Tourism and Major Events and Assistant Minister for Skills
Minister for Trade and Industry
Minister for Transport and Infrastructure
Minister for Veterans Affairs
Minister for WestConnex
Minister for Western Sydney
Minister for Women
Premier
Treasurer
Other

## Data-office use only (hidden)
Project /Program name | Responsible Minister | If other, specify | Lead Department | If other, specify | Project Sponsor Name | Project Sponsor Title | Project Sponsor Address | Project Sponsor Phone | Project Sponsor Email | Part of a Wider Program: (state name) | Interdependence with another project: (state name) | Project description | Objectives | Expected strategic benefits | Funding approval | Funding source | Funding details | Funding conditions | #REF! | #REF! | #REF! | Estimated Total Cost ($million) | #REF! | #REF! | Key Project Milestones (e.g. Funding approval, Project Commissioning, Project Operationalisation etc.) with estimated dates | #REF! | Current Project phase | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Project Registration, Risk Tier and Assurance Plan approved by (Senior Responsible Officer with the delegation to approve submission of form) | Title of Approver | Contact number of Approver | Date approved | Level of Government Priority | Explanatory Notes | Interface Complexity Risk | Explanatory Notes | Procurement Complexity Risk | Explanatory Notes | Agency Capability Risk | Explanatory Notes | Criticality of Service Risk | Explanatory Notes | Implementation Complexity Risk | Explanatory Notes | Rating - Level of Government Priority | Rating - Interface Complexity | Rating - Procurement Complexity | Rating - Agency Capability | Rating - Criticality of Service Complexity | Rating -Implementation Complexity | 0 | Risk rating | Total weighted score and corresponding risk range | Preliminary Risk Tier | Are there any reasons why the Preliminary risk rating determined above should be adjusted to be higher or lower on account of any additional risk considerations? Additional factors that could impact risk rating include, for example, risk of reputational damage, unknown project governance arrangements, lack of necessary project development plan and/or delivery skills and resources and critical or mandated start or completion date. | If Yes, please provide brief comments | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Preliminary Risk Tier | Based on the answer to Q4.01 does the Preliminary risk tier require to be adjusted? | Adjusted Risk Tier | #REF! | #REF! | #REF! | Gate 0 - Project Justification (refer Appendix 3 and 4 for more detail) | Month/Year or Q/Year | Gate 1 - Strategic Alignment gate (refer Appendix 3 and 4 for more detail) | Month/Year or Q/Year | Gate 2 - Business Case gate (refer Appendix 3 and 4 for more detail) | Month/Year or Q/Year | Gate 3 - Pre-tender/Pre-execution gate (refer Appendix 3 and 4 for more detail) | Month/Year or Q/Year | Gate 4 - Tender Evaluation gate (refer Appendix 3 and 4 for more detail) | Month/Year or Q/Year | Gate 5 - Pre-Commissioning gate (refer Appendix 3 and 4 for more detail) | Month/Year or Q/Year | Gate 6 - Post-Implementation gate (refer Appendix 3 and 4 for more detail) | Month/Year or Q/Year | Proposed Gateway Health Checks | #REF! | #REF! | #REF! | #REF! | #REF! | Has this proposal been discussed with NSW Policy & Budget Treasury Analyst | If yes, who is your Treasury Policy & Budget Analyst (Name)
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! |  | #REF! | #REF! | 0 | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | - | - | - | - | - | - | 0 |  |  |  | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | 0 | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0